## Portal Project Tracking Form
Note: the tracking sheet shown below can be adapted to include tasks in your organization's work plan.
Author: Jim Meyers, Developed February 8, 2016, jimmeyersdrph@gmail.com©
Patient Portal Project Management Tracking Form
|  |  | First 6 Months |  | Second 6 Months
Major Work Area | Activity | Point of Contact | Status | Comments | Status | Comments
1. Convene Patient Portal Project Team on a monthly basis |  |  | On Target
a. Meet Monthly with at least team, clinical, ops and IT portal project leaders in attendance.
b. Select Key Team Members
b. 1. Portal Overall Team Leader
b. 2. Portal Clinical Leader
b. 3. Portal Staff Support Leader
b. 4. Portal IT/IS Support Leader
c. Review Portal Use Data from Vendor at each meeting
2. Complete Senior Leader Update Reports
| a. Prepare patient portal dashboard |  | Not on Target
b. Present at regular times to senior leaders
3. Develop job descriptions for Patient Portal Project Manager and Portal Engagement Specialists, post positions, interview, hire | a. Set up job description for Patient Portal Supervisor |  | Immediate Attention
4. Develop portal quality assurance checklists - staff | a. Conduct quality audits on various features of the portal and features
5. Develop Workflows to each Portal Application
a. Appointments
b. Ask Your Provider Team
c. Refill Prescriptions
d. Download Visit Summary
6. Creation of training aides
a. Determine job aids needed
b. Develop short video aids
7. Access to outside resources that can help promote the patient portal with staff and patients
8. Purchase and use iPads in clinics to support patient engagement
a. Buy ipads
b. Load application function on ipads
c. Deploy securely to patients
9. Production of marketing materials, including educational handouts and videos, in English and Spanish | a) create handouts to be given to patients with instructions how to register and technical questions.
b) Production of posters for waiting area in colloboration with marketing department
c) Create a FAQ doc for patients to refer to with questions when using the portal.
10. Start special projects to improve current functionality and/or add more automated functionality such as real-time scheduling and SMS text option
11. Set up feedback stations--boxes, paper, pens for forms and surveys | a) Create patient portal surveys to be completed by providers and staff. The survey will be conducted monthly
12. Need consultation over liability for portal, and basic state requirements for storing and protecting PHI in cases of emergency—no cost
13. Develop language for banners for risk mitigation | a) Have verbage assigned to risk mitigation
14. Develop staff protocols for technical problems and emergencies | a) Send email to the assigned contact when the portal is down
15. Patient access to portal for minors
a. Develop Policies and Procedures
16. Spanish Version of Portal
a. Develop Policies and Procedures
b. Translations services needed?